## Sheet1
GOAL | OBJECTIVE | DEPT | TASK | START | END | COMPLETION | STATUS
1 | A | ADM | Conduct inter-rater reliability assessments on all validated risk/needs assessment tools at least bi-annually. | July 2020 | March 2023 | 50% | On Target
1 | A | ADM | Facilitate evidence-based practices briefcase trainings for supervisors. | August 2019 | October 2019 | 100% | Completed
1 | A | AFS | Implement case management standards.* | January 2018 | December 2021 | 100% | Completed
1 | A | AFS | Conduct quarterly reviews/audits of case plans.* | April 2020 | December 2021 | 100% | Completed
1 | A | AFS | Ensure case plan templates are in compliance with state and federal guidelines, while also using the risk-need-responsivity (RNR) model for medium and high-risk clients. | May 2020 | April 2021 | 100% | Completed
1 | A | AFS | Meet and confer with labor union on the potential impacts of the case management standards.* | January 2019 | July 2021 | 100% | Completed
1 | A | AFS | Revise and implement an evidence-based rewards and sanctions matrix for adult clients. | January 2018 | December 2020 | 100% | Completed
1 | A | JFS | Revise and implement an evidence-based rewards and sanctions matrix for juvenile clients. | January 2020 | June 2021 | 100% | Completed
1 | A | JFS | Implement case management standards for the juvenile division. | March 2020 | June 2021 | 100% | Completed
1 | A | JFS | Develop and implement the case management standards.* Previously referenced as Meet and Confer with labor union on the potential impacts of the case management standards | April 2020 | December 2021 | 100% | Completed
1 | A | JFS | Ensure case plan templates are in compliance with state and federal guidelines, while also using the risk-need-responsivity (RNR) model for medium and high-risk clients. | January 2020 | December 2020 | 100% | Completed
1 | A | JFS | Conduct quarterly reviews/audits of case plans. | January 2019 | Ongoing | 100% | Completed
1 | B | ADM | Develop protocols to oversee contract services and determine role clarification between GSA, fiscal, and contracts staff. | April 2020 | December 2022 | 75% | On Target
1 | B | ADM | Use the Correctional Programs Checklist to assess adherence of ACPD programs to evidence-based practices. | June 2020 | December 2023 | 0% | On Target
1 | B | ADM | Develop and implement processes to notify staff of changes in contracted services and service providers on an ongoing basis. | June 2020 | December 2020 | 100% | Completed
1 | B | ADM | Add the capability of reporting on all benchmarks/outcome measures outlined in the vendor contracts to Tyler Supervision or using other software. | January 2020 | June 2022 | 100% | Completed
1 | B | AFS | Create more in-person opportunities for providers to meet face to face with staff. | April 2019 | October 2020 | 100% | Completed
1 | B | AFS | Train staff to use Tyler Supervision to communicate with contracted and non-contracted community-based organizations. | October 2019 | June 2020 | 100% | Completed
1 | B | AFS | Establish policy and procedure guidelines for multidisciplinary team meetings and include them in meetings for high risk clients. | September 2020 | December 2021 | 100% | Completed
1 | B | JFS | Train and require staff to use Tyler Supervision to communicate with contracted and non-contracted community-based organizations. | June 2020 | December 2020 | 100% | Completed
1 | B | JFS | Establish policy and procedure guidelines for multidisciplinary team meetings. | March 2020 | December 2020 | 100% | Completed
1 | B | JFS | Create more in-person opportunities for providers to meet face to face with staff and direct staff to attend these opportunities. | November 2019 | Ongoing | 100% | Completed
1 | C | ADM | Develop a policy requiring staff to provide concrete services (bus passes, BART cards, food, etc.) to clients. | June 2018 | October 2020 | 100% | Completed
1 | C | AFS | Expand the Mental Health Collaborative Court to include adult clients with felony convictions. | November 2019 | December 2021 | 100% | Completed
1 | C | AFS | Establish criteria for specialized caseloads and parameters for case assignments to include the results from assessments.* | April 2020 | July 2021 | 100% | Completed
1 | C | AFS | Require staff to use Tyler Supervision and its provider portal to make referrals to services in the community and ensure client participation. | January 2019 | December 2020 | 100% | Completed
1 | C | AFS | Create a specialized mental health caseload unit--specifically SMI and Duel Diagnosis cases | April 2020 | July 2021 | 100% | Completed
1 | C | JFS | Develop a data system to track referrals and outcomes for juveniles not supervised by ACPD. | January 2020 | November 2021 | 100% | Completed
1 | C | JFS | Establish criteria for specialized caseloads and parameters for case assignments to include the results from assessments. | March 2020 | December 2020 | 100% | Completed
1 | C | JFS | Add a specialized mental health caseloads. | March 2020 | December 2021 | 100% | Completed
1 | D | ADM | Refer clients to eligible services in the community upon discharge. | August 2019 | January 2023 | 75% | On Target
1 | D | ADM | Develop and implement a discharge/transition planning model. | June 2020 | January 2023 | 75% | On Target
1 | D | ADM | Require vendors to detail all available transition services for clients upon discharge from probation supervision. | June 2020 | June 2022 | 100% | Complete
1 | D | ADM | Develop a resource packet and distribute to all clients prior to discharge. | June 2020 | April 2021 | 100% | Completed
1 | D | ADM | Establish a reentry unit. | August 2019 | March 2021 | 100% | Completed
1 | F | ADM | Evaluate the impact of having staff coached and trained on client outcomes. | February 2022 | February 2023 | 0% | On Target
1 | G | ADM | Identify restorative justice services in Alameda County; Identify service gaps; implement best practices | Jan 2021 | January 2023 | 25% | On Target
1 | G | ADM | Collect monthly data to assess staff success in addressing client Dynamic Factors criminogenic needs. | April 2020 | Feb 2022 | 100% | Completed
1 | G | ADM | Conduct a service gap analysis (map) for entire reentry process bi-annually. | July 2020 | September 2022 | 100% | Completed
1 | G | AFS | Develop and implement the Pre-Trial Services Program. | July 2019 | May 2020 | 100% | Completed
1 | G | AFS | Develop a plan to engage adult clients in civic and community engagement strategies. | January 2021 | January 2022 | 100% | Complete
1 | H | ADM | Conduct contract compliance audits of family reunification providers. | July 2020 | January 2022 | 100% | Complete
1 | H | ADM | Conduct family focus groups at least bi-annually. | July 2020 | March 2021 | 100% | Completed
1 | H | AFS | Establish collaborative meetings for Adult Field Services clients that include family and other natural supports, including a partner portal. | January 2020 | Sept 2022 | 100% | Complete
1 | H | AFS | Develop and implement family engagement activities (i.e. family night, parent orientation, etc.). | January 2021 | January 2022 | 100% | Completed
1 | H | AFS | Add family-specific components to case plans. | January 2018 | October 2021 | 100% | Completed
1 | H | JFS | Add family-specific components to case plans. | March 2020 | June 2021 | 100% | Completed
1 | H | JFS | Develop and implement family engagement activities (i.e. family night, parent orientation, etc.). | November 2019 | March 2021 | 100% | Completed
1 | H | JFac | Develop and implement family engagement activities (i.e. family night, parent orientation, etc.). | October 2019 | Ongoing | 100% | Completed
2 | A | ADM | Create resources (videos, brochures, interactive website) that explain probation processes and services to clients and develop plan that outlines communication strategy. | January 2020 | December 2022 | 100% | Complete
2 | A | AFS | Establish a Residential Multi-Service Program in Alameda County. | July 2022 | December 2023 | 25% | On Target
2 | A | AFS | Implement a behavior change model of supervision. | January 2020 | December 2020 | 100% | Completed
2 | A | AFS | Expand pre-release services for adults reentering from jail and prison, to include referrals completed prior to release. | June 2019 | October 2020 | 100% | Completed
2 | A | JFS | Implement a behavior change model of supervision. | April 2020 | September 2022 | 100% | Completed
2 | A | JFS | Expand pre-release reach-in services to youth reentering from Camp Sweeney, placement, or Juvenile Hall, to include referrals completed prior to release. | January 2017 | December 2021 | 100% | Completed
2 | A | JFac | Validate the detention assessment tool in Juvenile Hall. | October 2021 | April 2022 | 50% | On Target
2 | A | JFac | Implement a detention assessment tool in Juvenile Hall. | January 2020 | March 2020 | 100% | Completed
2 | A | JFac | Implement programming in Juvenile Hall to address criminogenic needs and life skills in ways that are appealing to youth. | January 2020 | December 2020 | 100% | Completed
2 | B | ADM | Implement a dosage-based supervision model. | July 2022 | December 2023 | 0% | On Target
2 | B | ADM | Create a resource directory on ACPD's home page. | December 2019 | June 2020 | 100% | Completed
2 | B | ADM | Train staff on the available resources in the community. | June 2020 | Ongoing | 100% | Completed
2 | B | AFS | Expand the CORE to create a “one-stop-shop” that would include services in a variety of reentry areas. | February 2020 | March 2023 | 25% | On Target
2 | B | AFS | Ensure a comprehensive array of cognitive behavioral intervention services for clients. | April 2020 | December 2022 | 75% | On Target
2 | B | JFS | Establish transitional day centers at recreation centers and community-based organizations to provide services to youth. | June 2022 | December 2023 | 100% | Completed
2 | B | JFS | Include clinicians in multidisciplinary team meetings for medium-to-high-risk juvenile clients. | April 2020 | December 2020 | 100% | Completed
2 | B | JFS | Ensure a comprehensive array of cognitive-based intervention services for juvenile clients. | January 2018 | December 2020 | 100% | Completed
2 | B | JFac | Include clinicians in multidisciplinary team meetings for medium-to-high-risk juvenile clients. | July 2019 | Ongoing | 100% | Completed
2 | C | ADM | Analyze housing need data from the intake process to better understand client housing needs. | June 2020 | January 2023 | 75% | On Target
2 | C | ADM | Hold focus groups with clients to understand their housing needs. | June 2020 | February 2021 | 100% | Completed
2 | C | ADM | Hold focus groups with landlords to understand concerns regarding renting to probation clients. | September 2020 | February 2021 | 100% | Completed
2 | C | ADM | Increase the number of contracted housing units available for probation clients. | January 2021 | June 2022 | 100% | Completed
2 | C | ADM | Create and hire a reentry housing coordinator position. | June 2019 | February 2021 | 100% | Completed
2 | C | AFS | Create and implement a Housing life skills training program which will include housing pamphlets, posters and other resources on housing options available. | March 2020 | March 2022 | 100% | Complete
2 | C | AFS | Revise the intake process to include an assessments of individuals’ housing needs. | April 2020 | December 2020 | 100% | Completed
2 | C | AFS | Direct staff to offer housing to clients based on need. | April 2020 | December 2020 | 100% | Completed
2 | C | JFS | Create and implement a housing life skills training program. | March 2020 | March 2022 | 100% | Completed
2 | C | JFS | Offer housing to clients based on their needs. | January 2020 | Ongoing | 100% | Completed
2 | C | JFac | Revise the intake process to include an assessments of juveniles’ housing needs. | February 2020 | December 2020 | 100% | Completed
2 | D | ADM | Create a mobile application for clients to access from their smart phones that lists all services provided through the probation department. | November 2019 | December 2022 | 75% | On Target
2 | D | AFS | Partner with Human Services or Social Services to ensure Medi-Cal is active prior to clients being released from custody. | January 2020 | June 2022 | 100% | Completed
2 | D | AFS | Ensure clients are routinely provided their vital documents (CA ID, SS card, Medi-Cal card) upon release from custody. | August 2019 | December 2020 | 100% | Completed
2 | D | AFS | Establish a process for adult homeless clients to receive vital documents. | February 2020 | December 2020 | 100% | Completed
2 | D | AFS | Ensure that clients leave custody with a specific plan that addresses their mental and physical health needs. | June 2020 | December 2020 | 100% | Completed
2 | D | AFS | Connect with clients while in custody to assess their needs for stabilization pre-release. | January 2020 | December 2020 | 100% | Completed
2 | D | AFS | Provide hygiene kits to clients upon release from custody, at intake and upon request. | September 2019 | Ongoing | 100% | Completed
2 | D | JFS | Establish a process for juvenile homeless clients to receive vital documents. | February 2020 | December 2022 | 75% | On Target
3 | A | ADM | Establish a critical incident stress management and peer support program to be staffed by ACPD personnel. | July 2022 | September 2023 | 75% | On Target
3 | A | ADM | Reclassify administrative specialist II to safety officer. | July 2019 | November 2019 | 100% | Completed
3 | A | AFS | Establish a weapons and safety committee to review current safety equipment and weapons and recommend new items. | April 2020 | March 2021 | 100% | Completed
3 | C | ADM | Assign recruitment committee members as mentors to new employees during their probationary period. | December 2019 | December 2022 | 50% | On Target
3 | C | ADM | Establish performance standards for each job classification within ACPD. | July 2019 | December 2022 | 75% | On Target
3 | C | ADM | Create a dedicated recruitment team. | Jan 2021 | December 2022 | 75% | On Target
3 | C | ADM | Revamp Volunteers in Probation (VIP) program. | July 2022 | December 2023 | 25% | On Target
3 | C | ADM | Develop a college student intern program under the Office of Human Resources. | July 2022 | December 2023 | 25% | On Target
3 | C | ADM | Revamp the new employee orientation and conduct it within 90 days of hire. | June 2019 | July 2019 | 100% | Completed
3 | C | ADM | Publicize job openings through career fairs, schools, and social media. | June 2019 | December 2019 | 100% | Completed
3 | C | ADM | Develop a tool to track the progress of recruitment efforts and measure recruitment of Affirmative Action Plan groups. | June 2019 | December 2020 | 100% | Completed
3 | C | ADM | Develop tool to track probationary and tenure statuses and retention of employees based on years with ACPD. | July 2019 | December 2020 | 100% | Completed
3 | D | ADM | Create a manual on the core competencies associated with the knowledge, skills, and abilities (KSAs) for all 81 job classifications. | June 2019 | December 2022 | 50% | On Target
3 | D | ADM | Assess employees’ professional development needs and coordinate annual course offerings to address those needs. | June 2019 | December 2022 | 50% | On Target
3 | D | ADM | Use annual performance evaluation to identify core competencies that need to be addressed through professional development. | June 2019 | December 2022 | 50% | On Target
3 | D | ADM | Offer elective trainings that address core competency requirements. | January 2019 | December 2022 | 25% | On Target
3 | D | ADM | Establish a leadership academy for executive managers. | July 2019 | December 2023 | 75% | On Target
3 | D | ADM | Establish a formal process for ongoing supervisor-employee progress reviews between annual performance evaluations. | February 2020 | December 2023 | 25% | On Target
3 | D | ADM | Establish a professional development academy for line and mid-level staff. | February 2018 | October 2019 | 100% | Completed
3 | D | ADM | Offer a new supervisors academy within first 90 days of hire or promotion. | January 2020 | December 2020 | 100% | Completed
3 | D | ADM | Announce training and conference opportunities as they become available. | January 2017 | Ongoing | 100% | Completed
3 | D | AFS | Create unit-specific performance measures and ensure applicable measures are consistent across divisions. | January 2020 | December 2020 | 100% | Completed
3 | D | JFS | Create unit-specific performance measures and ensure applicable measures are consistent across divisions. | April 2020 | December 2020 | 100% | Completed
3 | E | ADM | Implement effective reminder system for employee performance evaluation. | November 2019 | December 2022 | 75% | On Target
3 | E | ADM | Establish consistent appreciation efforts to acknowledge and celebrate ACPD employees. | January 2020 | December 2023 | 25% | On Target
3 | E | ADM | Establish and launch a new staff appreciation component to current recognition program. | January 2020 | March 2022 | 100% | Complete
3 | E | ADM | Implement interim effective reminder system for employee performance evaluation. | November 2019 | December 2020 | 100% | Completed
3 | E | ADM | Survey staff to measure the effectiveness of recognition and appreciation programs. | December 2019 | December 2020 | 100% | Completed
3 | F | ADM | Revise annual performance evaluation process and policy. | February 2020 | June 2021 | 100% | Completed
4 | A | ADM | Track time associated with the stages of policy development. | June 2019 | November 2021 | 100% | Complete
4 | A | ADM | Develop division-specific procedures, including accountability measures, to ensure staff are trained on new policies. | March 2020 | December 2020 | 100% | Completed
4 | A | ADM | Fully staff the Policy Unit. | January 2020 | September 2020 | 100% | Completed
4 | A | ADM | Develop division-specific procedures, including accountability measures, to ensure staff are trained on new policies. | March 2020 | December 2020 | 100% | Completed
4 | A | ADM | Develop a process for reporting implementation (training and dissemination) of new policies to the Policy Unit. | March 2020 | December 2020 | 100% | Completed
4 | A | ADM | Identify and track policy priorities on an ongoing basis by division. | January 2019 | August 2019 | 100% | Completed
4 | A | ADM | Formalize a process to identify training needs early in the policy development stage and prior to routing the policy to County Labor. | January 2019 | October 2019 | 100% | Completed
4 | A | ADM | Research and implement a policy management software. | June 2019 | March 2020 | 100% | Completed
4 | A | ADM | Revise the policy and procedures intranet page to include a more accessible layout and improved organization of policy manuals. | November 2019 | September 2020 | 100% | Completed
4 | A | ADM | Track policies identified for development. | June 2019 | December 2020 | 100% | Completed
4 | B | ADM | Hire a communications director. | December 2019 | September 2022 | 25% | On Target
4 | B | ADM | Create and implement a communication matrix/system. | January 2021 | June 2022 | 0% | On Target
4 | B | ADM | Establish methods for the dynamic exchange of information between units and divisions. | January 2021 | June 2022 | 0% | On Target
4 | B | ADM | Develop a communication policy that includes social media. | March 2020 | December 2022 | 75% | On Target
4 | B | ADM | Develop and administer annual external stakeholder survey. | August 2020 | September 2022 | 75% | On Target
4 | B | ADM | Create a departmental newsletter. | January 2020 | December 2020 | 100% | Completed
4 | B | ADM | Develop a communication workgroup that would oversee the annual staff survey. | December 2020 | June 2021 | 100% | Completed
4 | B | ADM | Develop and implement an internal probation bulletin board page that would include probation-related research articles, job tutorials, standard operating procedures, officer-of-the-day calendar for all divisions, locations, and units, unit rosters and contact information, staff meeting agendas & minutes, and professional development training opportunities. | January 2021 | January 2022 | 100% | Completed
4 | C | ADM | Regularly publish performance measure data internally and externally. | May 2020 | December 2022 | 75% | On Target
4 | C | ADM | Hire an administrator for Tyler Supervision. | November 2019 | December 2020 | 100% | Completed
4 | C | ADM | Create a research unit. | November 2018 | November 2019 | 100% | Completed
4 | C | ADM | Develop quality assurance protocols and procedures. | January 2020 | March 2021 | 100% | Completed
4 | C | ADM | Establish a quality assurance process for all publicly-reported data. | December 2019 | June 2020 | 100% | Completed
4 | C | ADM | Create a quality assurance unit. | January 2020 | December 2020 | 100% | Completed
4 | C | ADM | Perform quality assurance checks on data from Tyler Supervision. | November 2019 | June 2020 | 100% | Completed
4 | C | ADM | Provide PowerBi licenses for all relevant classifications and develop advanced training and support systems | January 2020 | December 2020 | 100% | Completed
4 | C | ADM | Create unit specific and job-specific dashboards. | June 2020 | December 2020 | 100% | Completed
4 | C | ADM | Develop and implement PROBSTAT. | December 2019 | December 2020 | 100% | Completed
4 | C | ADM | Establish internal expert on PowerBI for ongoing support. | January 2020 | December 2020 | 100% | Completed
4 | C | ADM | Provide training to units on performance measurement. | January 2020 | December 2020 | 100% | Completed
4 | C | ADM | Develop and report on strategic plan performance measurement. | April 2019 | Ongoing | 100% | Completed
4 | C | AFS | Fully implement Tyler Supervision. | January 2019 | June 2020 | 100% | Completed
4 | C | AFS | Hold standing meetings with labor unions regarding Tyler Supervision and COMPAS implementation. | February 2019 | Ongoing | 100% | Completed
4 | C | JFS | Hold standing meetings with labor unions regarding TS implementation. | August 2020 | April 2021 | 100% | Completed
4 | C | JFS | Fully implement Tyler Supervision. | August 2020 | December 2020 | 100% | Completed
4 | C | JFS | Establish Tyler Supervision Core Team for Juvenile Field Services. | October 2019 | December 2019 | 100% | Completed
4 | C | JFac | Establish Tyler Supervision core team for Juvenile Facilities. | January 2020 | June 2020 | 100% | Completed
4 | C | JFac | Fully implement Tyler Supervision. | August 2020 | December 2020 | 100% | Completed
4 | D | ADM | Collect quantitative data to demonstrate skill acquisition and outcomes related to training staff in evidence-based practices. | February 2022 | February 2023 | 0% | On Target
4 | D | ADM | Create a contracts unit. | November 2018 | January 2020 | 100% | Completed
4 | D | ADM | Develop a survey that allows clients to provide feedback on provider services and require contractors to administer survey. | January 2021 | June 2022 | 100% | Complete
4 | D | ADM | Establish necessary points of collaboration between the EBP Unit, Contracts Unit, and Research Unit. | November 2018 | June 2020 | 100% | Completed
4 | D | ADM | Participate in the Alameda County Results First initiative with other criminal justice partners. | December 2018 | July 2020 | 100% | Completed
4 | D | ADM | Develop a policy for conducting internal research studies, including access to external research databases. | November 2019 | December 2020 | 100% | Completed
4 | D | ADM | Establish consistent performance measures and definitions in RFPs and contracts based on type of service being provided. | October 2018 | December 2020 | 100% | Completed
4 | D | ADM | Create an evidence-based practices unit. | November 2018 | December 2021 | 100% | Completed
4 | D | ADM | Develop a standardized process for collecting and reporting on performance measure data from contracted providers. | June 2020 | Sept 2022 | 100% | Completed
4 | D | ADM | Develop corrective action plans for contracted providers that don't meet their reporting requirements. | October 2018 | Ongoing | 100% | Completed
4 | D | ADM | Provide ongoing training to staff on evidence-based practices. | December 2019 | March 2022 | 100% | Complete
4 | D | ADM | Solicit input from Research and Evidence-based Practices Units on development of new RFPs. | October 2018 | Ongoing | 100% | Completed
4 | E | ADM | Hold regular collaboration meetings between legislation, policy, research, and division reps to discuss upcoming data needs. | June 2020 | June 2022 | 100% | Completed
4 | E | ADM | Continue to produce annual Realignment reports and produce fact sheets to disseminate publicly. | November 2018 | June 2022 | 100% | Completed
4 | E | ADM | Develop a process to track and measure internal data requests. | April 2020 | April 2021 | 100% | Completed
4 | E | ADM | Establish process to continuously monitor and update data collection, reporting, and data collection needs. | January 2020 | January 2021 | 100% | Completed
4 | E | ADM | Use data to evaluate outcomes against departmental performance measures. | January 2020 | December 2020 | 100% | Completed
4 | E | ADM | Develop data dictionary for all data dashboards released. | January 2020 | June 2021 | 100% | Completed
4 | E | ADM | Develop definitions and process for reporting on client outcomes, including recidivism. | January 2020 | December 2020 | 100% | Completed
5 | A | ADM | Create matrix tracking all ACPD initiatives with external partners. | November 2018 | April 2019 | 100% | Completed
5 | A | ADM | Develop a shared vision of public safety based on feedback from and collaboration with JJDPC and CCPEC. | January 2020 | Ongoing | 100% | Completed
5 | B | ADM | Establish policies, procedures, and oversight for data-sharing agreements with external agencies. | January 2020 | December 2021 | 100% | Completed
5 | B | ADM | Provide information about publicly available data and data request processes on ACPD website. | October 2019 | December 2019 | 100% | Completed
5 | B | ADM | Develop policy and process for sharing data externally (through website, DSAs, etc.) | January 2020 | December 2021 | 100% | Completed
5 | B | ADM | Upload and regularly update information on ACPD's website and intranet. | October 2019 | Ongoing | 100% | Completed
5 | C | ADM | Develop and implement an anonymous client survey that solicits feedback from clients about their experience on probation and how ACPD can improve its service delivery. | June 2019 | December 2022 | 75% | On Target
5 | C | ADM | Analyze data on adult service usage and outcomes from service providers using Tyler Supervision. | June 2020 | June 2022 | 100% | Complete
5 | C | ADM | Analyze data on service usage and outcomes for juvenile clients and at-promise youth using Tyler Supervision (provider portal being stood up), Mobius (working with them on needed changes), and Results First. | August 2020 | December 2021 | 100% | Complete
5 | C | AFS | Deploy Tyler/Enterprise Supervision Supervision App | August 2020 | December 2022 | 75% | On Target
5 | C | AFS | Deploy Prime. | January 2019 | January 2020 | 100% | Completed
5 | C | JFS | Deploy Tyler/Enterprise Supervision Supervision App | August 2020 | December 2022 | 75% | On Target
5 | C | JFac | Provide tablets to all youth in Juvenile Hall and Camp Sweeney for academic and incentive programming. | September 2019 | February 2020 | 100% | Completed
6 | A | ADM | Perform a gap analysis on policy, training, initiatives, service contracts, etc. related to victim support services. | January 2021 | June 2022 | 0% | On Target
6 | A | ADM | Expand departmental policies related to victim support, including notification of victims rights and creating victim safety plans. | January 2021 | June 2022 | 0% | On Target
6 | A | ADM | Assign victim services liaison responsibilities to juvenile and adult services ombudsman. | January 2021 | June 2022 | 0% | On Target
6 | A | ADM | Add resources regarding victims services to ACPD website. | November 2019 | December 2019 | 100% | Completed
6 | A | AFS | Develop a victim support model for ACPD in coordination with the District Attorney's Office. Expand departmental policies related to victim support, including notification of victims rights and defining expectations around victim safety plans. | January 2020 | September 2022 | 100% | Completed
6 | C | AFS | Develop auditing process for batterers intervention programs. | January 2020 | December 2020 | 100% | Completed