## Project Timeline
1
2 |  |  | Strategic Plan Update Q4 2022 Adult Field Services Division Project Lead: Deputy Chief Chris Pedrotti |  | Phase 1: Oct 2019--Dec 2020 Phase 2: Jan 2021--June 2022 Phase 3: July 2022--Dec 2023 |  | Percent (%) Complete |  |  |  | Complete: BLUE On Target: GREEN At Risk: YELLOW Past Due: RED | (New Tab) Bargaining Unit (Pending with Labor) | Last updated: 9/22/2022
3 | GOAL | OBJ | TASK | CONTACT PERSON | START DATE | END DATE | 25% | 50% | 75% | 100% | STATUS | Labor Status | NOTES
4 | PHASE 1 TASKS
5
6 | PHASE 2 & 3 TASKS
7 | 2 | A | Establish a Residential Multi-Service Program in Alameda County. | Chris Pedrotti & Shauna Conner | January 2020 July 2022 | September 2021 December 2023 |  |  |  |  | On Target |  | CCPEC approved funding; work still being done/some on hold for now. Work is still being done. CCPEC is in prefunding. Not On-Target for December. Moved to Phase 3. Communication with GSA regarding a space request of current capital (offices/building) stock availability. | Discuss with Chief about Moving Shauna's items to admin
8 | 2 | B | Expand the CORE to create a “one-stop-shop” that would include services in a variety of reentry areas. | Shauna Conner | February 2020 | June 2021 March 2022 September 2022 March 2023 |  |  |  |  | On Target |  | Recently got TA opportunity with Opportunity Accelerator (Harvard). Doors expected to open March 2023. RFP held due to issues with GSA
9 | 2 | B | Ensure a comprehensive array of cognitive behavioral intervention services for clients. | Shereen Khan Shauna Conner | April 2020 | December 2021 June 2022 September 2022 December 2022 |  |  |  |  | On Target |  | Department implemented T4C; Carey Guides are available for DPOs to provide direct services; CORE provides several groups for clients in conjuction with CBO programs; Five Keys SSA under negotiation. Tentatively scheduled to start 11/1/2022.
10 | 5 | C | Deploy Tyler/Enterprise Supervision Supervision App | Adrienne Chambers/ Sherron Lee | August 2020 | December 2020 September 2021 December 2021 June 2022 September 2022 December 2022 |  |  |  |  | On Target |  | Robert A stated Tyler does not have same functions as Adult and will require development; Tyler is building own app similar to Tyler; Tyler won't give same functionality for Juvenile as it does for Adult. Decision point to move forward with Tyler Sup. Adrienne to follow up with Tyler to see if this is something that can be done. If so, request extension to June 2022, DCPO is testing app. Decision is to move forward with the Enterprise Supervision app, previously known as Tyler. Memo sent to Alicia & Chris for review (for AFS an JFS can roll this out). Training is impacted right now, so Sherron has a suggested plan, before moving forward to use. | Added to AFS (new tasks for AFS) had PRIME previously.
11 | * | * | * Indicates item is in meet and confer process
12 | COMPLETED TASKS
13 | 1 | A | Implement case management standards.* | Chris Pedrotti | January 2018 | December 2020 July 2021 December 2021 |  |  |  |  | Completed |  | BOS approved Caseload Management Standards, Implementation plan initiated. Full implementation by 12/21. We are set to meet the December 2021 deadline.
14 | 1 | A | Conduct quarterly reviews/audits of case plans.* | Directors | April 2020 | January 2021 July 2021 November 2021 December 2021 |  |  |  |  | Completed |  | Awaiting case plan training; process established and plan in place; request extension by three months once policy is done. NOT On-Target. Set to be implemented by December 2021. This item is now completed.
15 | 1 | A | Ensure case plan templates are in compliance with state and federal guidelines, while also using the risk-need-responsivity (RNR) model for medium and high-risk clients. | Chris Pedrotti | May 2020 | December 2020 April 2021 |  |  |  |  | Completed |  | This has been corrected and completed in March
16 | 1 | A | Meet and confer with labor union on the potential impacts of the case management standards.* | Chris Pedrotti | January 2019 | December 2020 July 2021 |  |  |  |  | Completed |  | Got fact finding report; awaiting next steps; request extension by three months
17 | 1 | A | Revise and implement an evidence-based rewards and sanctions matrix for adult clients. | Chris Pedrotti | January 2018 | December 2020 |  |  |  |  | Completed |  | Matrix has been updated and training was held in December
18 | 1 | B | Create more in-person opportunities for providers to meet face to face with staff. | Lisa Abernathy & Shauna Conner | April 2019 | October 2020 |  |  |  |  | Completed |  | Meetings being held; this was implemented in October
19 | 1 | B | Train staff to use Tyler Supervision to communicate with contracted and non-contracted community-based organizations. | Craig Emmons | October 2019 | June 2020 |  |  |  |  | Completed |  | Training done for all providers and being implemented fully
20 | 1 | B | Establish policy and procedure guidelines for multidisciplinary team meetings and include them in meetings for high risk clients. | Chris Pedrotti | September 2020 | December 2020 June 2021 December 2021 |  |  |  |  | Completed |  | Doing case conferencing with treatment team; and has begun on several fronts with small groups. request extension through June--Extension through Dec. Expanded access to Partner Portal and enhanced communications…establishing SUD clinicians at PC. Have all stakeholders actively participating, Does not need a separate policy, also covered in the DV Policy.
21 | 1 | C | Expand the Mental Health Collaborative Court to include adult clients with felony convictions. | Chris Pedrotti | November 2019 | December 2020 June 2021 December 2021 |  |  |  |  | Completed |  | Had discussions with judge about this; impacted by court closures; request extension until June for follow up with Judge Smiley. DA's office not willing to commit to expanding courts. Expanding through pretrial has been discussed. Request extension through December 2021. This will not (need an extension). This is something that is outside our authority, as this rests with the courts and justice partners. All areas pertaining to ACPD are completed.
22 | 1 | C | Establish criteria for specialized caseloads and parameters for case assignments to include the results from assessments.* | Chris Pedrotti | April 2020 | June 2020 December 2020 July 2021 |  |  |  |  | Completed | Pending Labor | Pertains to Sex Offender Policy and DV Policy.
23 | 1 | C | Require staff to use Tyler Supervision and its provider portal to make referrals to services in the community and ensure client participation. | Directors | January 2019 | December 2020 |  |  |  |  | Completed |  | Referrals are being made through the portal
24 | 1 | C | Create a specialized mental health caseload unit--specifically SMI and Duel Diagnosis cases | Chris Pedrotti | April 2020 | June 2020 December 2020 July 2021 |  |  |  |  | Completed |  | DPO for Prop 47 hired and has a small caseload;
25 | 1 | G | Develop and implement the Pre-Trial Services Program. | Delean Carson Walker & Shauna Conner | July 2019 | May 2020 |  |  |  |  | Completed |  | Went live Jan 21st; work will be ongoing
26 | 1 | G | Develop a plan to engage adult clients in civic and community engagement strategies. | Shauna Conner & Alexa Young | January 2021 | January 2022 |  |  |  |  | Complete |  | Focus/goal to connect clients to natural resources in the community, fund outreach efforts and keep clients apprised of legislation and initiatives that directly impact the reentry community. Next event Resource fair scheduled July 30th in conjunction with Supervisor Carson's office.
27 | 1 | H | Establish collaborative meetings for Adult Field Services clients that include family and other natural supports, including a partner portal. | Chris Pedrotti | January 2020 | June 2021 March 2022 Sept 2022 |  |  |  |  | Complete |  | Collaborative meetings have been instituted and are occurring in CORE as well with Juvenile Operations. Partner Portal collaboration is now in place. A formal MDT process is delineated in the Sex Offender/DV Draft Policy (Containment Model), currently with county counsel. MDT's style trainings to be available for staff to assist in administering collaborative MDT meetings as necessary. The verbiage for this collaborative modeling has gone through a couple of iterations (CDC language, to MDT, etc.).
28 | 1 | H | Develop and implement family engagement activities (i.e. family night, parent orientation, etc.). | Shauna Conner & Directors | January 2021 | January 2022 |  |  |  |  | Completed |  | Activities completed in December. Have a plan for quarterly activities. Completed.
29 | 1 | H | Add family-specific components to case plans. | Chris Pedrotti | January 2018 | December 2020 April 2021 October 2021 |  |  |  |  | Completed |  | Family specific components will be through R&S process; testing is happening this week; should be done by end of April. Will be completed in October. Everything is operational, but full implementation will come with the RNS. Mark as complete when training is completed.
30 | 2 | A | Implement a behavior change model of supervision. | Chris Pedrotti | January 2020 | December 2020 |  |  |  |  | Completed |  | Updates are in TS and this is now happening
31 | 2 | A | Expand pre-release services for adults reentering from jail and prison, to include referrals completed prior to release. | Shauna Conner & Chris Pedrotti | June 2019 | October 2020 |  |  |  |  | Completed |  | Connections have been made with ACSO Transition Team to improve communication and referral process for adults transition from the jail. Tablet process recently implemented. Implementing COMPAS assessment and Pathways for clients who will not enter prison
32 | 2 | C | Create and implement a Housing life skills training program which will include housing pamphlets, posters and other resources on housing options available. | Shauna Conner & Tyler Zatcoff | March 2020 | June 2020 July 2021 November 2021 March 2022 |  |  |  |  | Complete |  | Connecting with CORE to provide housing life skills program; identified components for life skills program. This is part of the housing program and is connected withJFS item 2C. Handled by Reentry and complete
33 | 2 | C | Revise the intake process to include an assessments of individuals’ housing needs. | Chris Pedrotti | April 2020 | December 2020 |  |  |  |  | Completed |  | Report tracker in production; referrals being done at pre-release and investigation levels; complete as of Nov
34 | 2 | C | Direct staff to offer housing to clients based on need. | Directors | April 2020 | December 2020 |  |  |  |  | Completed |  | This is regularly happening
35 | 2 | D | Partner with Human Services or Social Services to ensure Medi-Cal is active prior to clients being released from custody. | Chris Pedrotti | January 2020 | June 2022 |  |  |  |  | Completed |  | Have pre-release process in place for prisons and SRJJ; Have SSA co-located in facilities once a week; begun billing for MAA; measures built into TS to monitor
36 | 2 | D | Ensure clients are routinely provided their vital documents (CA ID, SS card, Medi-Cal card) upon release from custody. | Christy Henzi | August 2019 | December 2020 |  |  |  |  | Completed |  | Process is in place; if clients do not receive it there is a process for document transition to Probation
37 | 2 | D | Establish a process for adult homeless clients to receive vital documents. | Christy Henzi | February 2020 | December 2020 |  |  |  |  | Completed |  | Process is being conducted by ACPD and is in place
38 | 2 | D | Ensure that clients leave custody with a specific plan that addresses their mental and physical health needs. | Christy Henzi | June 2020 | December 2020 |  |  |  |  | Completed |  | Have a case plan and the portal to address their physical and mental health needs
39 | 2 | D | Connect with clients while in custody to assess their needs for stabilization pre-release. | Shauna Conner | January 2020 | December 2020 |  |  |  |  | Completed |  | Processes established with Pathways and SRJ
40 | 3 | A | Establish a weapons and safety committee to review current safety equipment and weapons and recommend new items. | Christy Henzi & Deandre Lewis | April 2020 | June 2020 March 2021 |  |  |  |  | Completed |  | Memo was sent out; Chief approved committee members and it is now established
41 | 3 | D | Create unit-specific performance measures and ensure applicable measures are consistent across divisions. | Chris Pedrotti, Chris Pedrotti, & Laura Agnich | January 2020 | December 2020 |  |  |  |  | Completed |  | Part of PROBSTAT process next meeting in Feb
42 | 4 | C | Fully implement Tyler Supervision. | Robert Ambroselli | January 2019 | June 2020 |  |  |  |  | Completed |  | Ongoing work to troubleshoot issues as they come up
43 | 5 | C | Deploy Prime. | Dennis Bradshaw | January 2019 | January 2020 |  |  |  |  | Completed
10 | 6 | A | Develop a victim support model for ACPD in coordination with the District Attorney's Office. Expand departmental policies related to victim support, including notification of victims rights and defining expectations around victim safety plans. | Chris Pedrotti | January 2020 | June 2022 September 2022 |  |  |  |  | Completed |  | Established a process to comply with Marci's law at pre-trial stage. Have process in place for Marci's law. Need to document engagement and support for victims. No longer doing pretrial assessment. Directly related to Pretrial and with end of assessments no longer applicable
44 | 6 | C | Develop auditing process for batterers intervention programs. | Adriana Manzano | January 2020 | December 2020 |  |  |  |  | Completed |  | Standardized certification process and auditing cycles
45 | ONGOING TASKS
46 | 2 | D | Provide hygiene kits to clients upon release from custody, at intake and upon request. | Christy Henzi | September 2019 | Ongoing |  |  |  |  | Completed
47 | 4 | C | Hold standing meetings with labor unions regarding Tyler Supervision and COMPAS implementation. | Chris Pedrotti & Karen Baker | February 2019 | Ongoing |  |  |  |  | Completed