## Project Timeline
1 |  |  | Strategic Plan Update 4 2022 Juvenile Field Services Division Project Lead: Assistant Chief Brian Ford |  | Phase 1: Oct 2019--Dec 2020 Phase 2: Jan 2021--June 2022 Phase 3: July 2022--Dec 2023 |  | Percent (%) Complete |  |  |  | Complete: BLUE On Target: GREEN At Risk: YELLOW Past Due: RED | (New Tab) Bargaining Unit (Pending with Labor) | Last updated:9/22/22
2 | GOAL | OBJ | TASK | CONTACT PERSON | START DATE | END DATE | 25% | 50% | 75% | 100% | STATUS | Labor Status | NOTES
3 | PHASE 1 TASKS
4 | PHASE 2 & 3 TASKS
5 | 2 | D | Establish a process for juvenile homeless clients to receive vital documents. | Alicia Mitchell | February 2020 | December 2020 June 2021 October 2021 March 2022 June 2022 December 2022 |  |  |  |  | On Target |  | Youth getting some vital documents but there needs to be a formal process; work group will be formed to develop written protocol
6 | 5 | C | Deploy Tyler/Enterprise Supervision Supervision App | Adrienne Chambers/ Sherron Lee | August 2020 | December 2020 September 2021 December 2021 June 2022 September 2022 December 2022 |  |  |  |  | On Target |  | Robert A stated Tyler does not have same functions as Adult and will require development; Tyler is building own app similar to Tyler; Tyler won't give same functionality for Juvenile as it does for Adult. Decision point to move forward with Tyler Sup. Adrienne to follow up with Tyler to see if this is something that can be done. If so, request extension to June 2022, DCPO is testing app. Decision is to move forward with the Enterprise Supervision app, previously known as Tyler. Memo sent to Alicia & Chris for review (for AFS an JFS can roll this out). Training is impacted right now, so Sherron has a suggested plan, before moving forward to use. | Add to AFS
7 | COMPLETED TASKS
8 | 1 | A | Revise and implement an evidence-based rewards and sanctions matrix for juvenile clients. | Alicia Mitchell | January 2020 | August 2020 December 2020 June 2021 |  |  |  |  | Completed | Pending Labor | Policy is written; Additional efforts made to seek DPO input on meaningful incentives to provide clients. Draft submitted to Policy unit. Labor Status should be updated to "Pending Labor".
9 | 1 | A | Implement case management standards for the juvenile division. | Adrienne Chambers | March 2020 | June 2021 |  |  |  |  | Completed | Pending Labor | Started negotiation process with ACMEA
10 | 1 | A | Develop and implement the case management standards.* Previously referenced as Meet and Confer with labor union on the potential impacts of the case management standards | Brian Ford | April 2020 | December 2020 April 2021 December 2021 |  |  |  |  | Completed | Pending Labor | Started negotiation process with ACMEA; Meeting was rescheduled, Went to Labor 1/13/21. ACMEA fine, Malia was out. Heard from Malia saying to explore with our PO's. Still waiting to hear from Teamsters.
11 | 1 | A | Ensure case plan templates are in compliance with state and federal guidelines, while also using the risk-need-responsivity (RNR) model for medium and high-risk clients. | Adrienne Chambers | January 2020 | December 2020 |  |  |  |  | Completed |  | Task is completed as the template is in place; training will be completed for all staff in 2021
12 | 1 | B | Train and require staff to use Tyler Supervision to communicate with contracted and non-contracted community-based organizations. | Adrienne Chambers | June 2020 | December 2020 |  |  |  |  | Completed |  | S. Lee conducted training, G. Gallo manages provider portal
13 | 1 | B | Establish policy and procedure guidelines for multidisciplinary team meetings. | Adrienne Chambers | March 2020 | December 2020 |  |  |  |  | Completed |  | Completed
14 | 1 | C | Develop a data system to track referrals and outcomes for juveniles not supervised by ACPD. | Laura Agnich | January 2020 | December 2020 June 2021 November 2021 |  |  |  |  | Completed |  | Mobius providing reports for DPN providers, still building AI portion, still seeking estimated completion date. Research indicates that this is now complete. Mobius has developed quarterly reporting capabilities and continues to do development work to improve data tracking using statistical modeling.
15 | 1 | C | Establish criteria for specialized caseloads and parameters for case assignments to include the results from assessments. | Adrienne Chambers | March 2020 | December 2020 |  |  |  |  | Completed |  | Caseloads assigned based on risk assessments; only specialized caseloads are gender specific
16 | 1 | C | Add a specialized mental health caseloads. | Adrienne Chambers | March 2020 | December 2021 |  |  |  |  | Completed |  | Existing partnerships and services in place to assist this population. The cases that have youth with specialized needs are dispersed.
17 | 1 | H | Add family-specific components to case plans. | Directors | March 2020 | June 2021 |  |  |  |  | Completed | Pending Labor | Started negotiation process with ACMEA
18 | 1 | H | Develop and implement family engagement activities (i.e. family night, parent orientation, etc.). | Alicia Mitchell | November 2019 | December 2020 March 2021 |  |  |  |  | Completed |  | A workgroup to develop a family engagement workshop series has been created. Family engagement activity scheduled for June 25th
19 | 2 | A | Implement a behavior change model of supervision. | Adrienne Chambers & Alicia Mitchell | April 2020 | December 2020 June 2021 October 2021 December 2021 June 2022 September 2022 |  |  |  |  | Completed |  | Moved to JFS: Transition Center--Curriculum for training has been developed; training to start in September, Delayed due to BSCC visits, Need to meet with facilities staff to align star goals with success plan goals. Scheduled for training in March 2022. Information sessions completed. Item tied to case management policy. Completed final informational sessions for success plan, which is how this is being tracked. Staff are completing success plans for youth. Doing this in facilities per TItle 15. Expectation is for staff to do this. Will do in community supervision. Case Management Policy is pending labor.
20 | 2 | B | Establish transitional day centers at recreation centers and community-based organizations to provide services to youth. | Brian Ford | June 2022 | August 2020 December 2020 June 2021 December 2023 |  |  |  |  | Completed |  | Decision to not move forward with this task because CBOs are currently providing services to youth through our DPN partnerships. Day and Recreation Centers are already in place through REACH Ashland, Eden Youth & Family Center in Hayward.
21 | 2 | B | Include clinicians in multidisciplinary team meetings for medium-to-high-risk juvenile clients. | Adrienne Chambers | April 2020 | December 2020 |  |  |  |  | Completed |  | Behavioral health clinicians are currently involved in this process and it is happening regularly (CFTs, SOS and Success Team meetings)
22 | 2 | A | Expand pre-release reach-in services to youth reentering from Camp Sweeney, placement, or Juvenile Hall, to include referrals completed prior to release. | Adrienne Chambers Alicia Mitchell | January 2017 | June 2020 July 2021 December 2021 |  |  |  |  | Completed |  | Item moved to JFS in Q2- The TC DPO reviews the Intake Questionnaire and identifies stabilization needs. The TC DPO participates in the care coordination meetings and uses information derived from there to aid in producing a TC re-entry plan. Additionally, there is a 1 pm daily MDT with all TC partners that allows them to discuss youth scheduled to appear for Detention Hearings, to ensure all reentry efforts are solidified and documented prior to the youth's release from custody. This meeting will be opened to all pertinent internal partners who have meaningful information to contribute to the conversation. Item complete as now providing reentry services to all youth
23 | 2 | B | Ensure a comprehensive array of cognitive-based intervention services for juvenile clients. | Brian Ford | January 2018 | December 2020 |  |  |  |  | Completed |  | All DPN contracts include Cognitive Behavioral programming; all contracts being extended 2 additional years; CBT contracts also through JJCPA providers
24 | 2 | C | Create and implement a housing life skills training program. | Adrienne Chambers | March 2020 | July 2021 December 2021 March 2022 |  |  |  |  | Completed |  | In Research-FISH. Also with Adults, reentry working on this. Aligned with Admin task
25
26 | 3 | D | Create unit-specific performance measures and ensure applicable measures are consistent across divisions. | Adrienne Chambers & Laura Agnich | April 2020 | December 2020 |  |  |  |  | Completed |  | Part of PROBSTAT next meeting in Feb
27 | 4 | C | Hold standing meetings with labor unions regarding TS implementation. | Brian Ford | July 2020 August 2020 | June 2020 April 2021 |  |  |  |  | Completed |  | Ongoing standing item on the LMC
28 | 4 | C | Fully implement Tyler Supervision. | Adrienne Chambers | June 2020 August 2020 | December 2020 |  |  |  |  | Completed |  | TS went live in Oct; work ongoing
29 | 4 | C | Establish Tyler Supervision Core Team for Juvenile Field Services. | Brian Ford | October 2019 | December 2019 |  |  |  |  | Completed
30 | ONGOING TASKS
31 | 1 | A | Conduct quarterly reviews/audits of case plans. | Jenifer Brown | January 2019 | Ongoing |  |  |  |  | Completed
32 | 1 | B | Create more in-person opportunities for providers to meet face to face with staff and direct staff to attend these opportunities. | Adrienne Chambers | November 2019 | Ongoing |  |  |  |  | Completed |  | Had previous meetings already to get this started; delayed to due COVID; held DPN meetings virtually and will be ongoing with staff (include DPOs)
33 | 2 | C | Offer housing to clients based on their needs. | Ryan McCreary | January 2020 | Ongoing |  |  |  |  | Completed |  | Breaking barriers; referring clients to housing providers; pamphlet created and given to youth