## Project Timeline
|  |  | Strategic Plan Update Q4 2021 Juvenile Facilities Division Project Lead: Deputy Chief Ian Long |  | Phase 1: Oct 2019--Dec 2020 Phase 2: Jan 2021--June 2022 Phase 3: July 2022--Dec 2023 |  | Percent (%) Complete |  |  |  | Complete: BLUE On Target: GREEN At Risk: YELLOW Past Due: RED | (New Tab) Bargaining Unit (Pending with Labor) | 2022-01-01
| GOAL | OBJ | TASK | CONTACT PERSON | START DATE | END DATE | 25% | 50% | 75% | 100% | STATUS | Labor Status | NOTES
PHASE 1 TASKS
PHASE 2 & 3 TASKS
1 | 2 | A | Validate the detention assessment tool in Juvenile Hall. | Laura Chavez | December 2020 October 2021 | December 2021 April 2022 |  |  |  |  | On Target |  | Research is working with staff to ensure proper data entry into Tyler Supervision; Validation study would take 6+ months to fully complete; Request to extend to June 2021. Development work prioritized on Tyler Supervision. Request extension on the validation of the tool. 12 months of data needed. Request start date to October 2021. To be completed April 2022. Testing on December 27. Laura: The research team examined all 2021 JDRAI data and determined that our sample size is too small to do a full validation study at this time. However, we produced a report that we are sharing with executive leadership next Friday and which will be shared with the Chief. The report includes analysis of JDRAI scores, overrides and mandatory detentions. Since the number of releases was too small for a validation study, this is the best we can do at this time for this item! Follow up w/ Laura 3/3/2022 -The Research team conducted an in-depth analysis of JDRAI data for 2021, presented findings to executive leadership and routed the final report to Chief. We don’t, however, have a large enough sample size of releases to validate the tool at this time. We will need at least one more year of data (and, likely at least 2 years) in order to have a large enough sample to calculate statistical significance for failure to appear and re-arrest rates in order to conduct a validation study.
COMPLETED TASKS
2 | 2 | A | Implement a detention assessment tool in Juvenile Hall. | Ian Long/James Rivers | January 2020 | March 2020 |  |  |  |  | Completed
3 | 2 | A | Implement programming in Juvenile Hall to address criminogenic needs and life skills in ways that are appealing to youth. | Ian Long/James Rivers | January 2020 | December 2020 |  |  |  |  | Completed |  | Providing ART and One circle programs. Still needs to train 60 staff in BITS. In October 2020, 8 staff completed Courage to Change training and have received journals for individuals and group CBT programs
4 | 2 | C | Revise the intake process to include an assessments of juveniles’ housing needs. | James Rivers/Ian Long | February 2020 | December 2020 |  |  |  |  | Completed |  | New classification policy started in Feb; training completed for new process
5 | 4 | C | Establish Tyler Supervision core team for Juvenile Facilities. | Ian Long | January 2020 | June 2020 |  |  |  |  | Completed
6 | 4 | C | Fully implement Tyler Supervision. | Brian Ford | June 2020 August 2020 | December 2020 |  |  |  |  | Completed |  | TS went live, work ongoing as needed
7 | 5 | C | Provide tablets to all youth in Juvenile Hall and Camp Sweeney for academic and incentive programming. | Ian Long | September 2019 | February 2020 |  |  |  |  | Completed
ONGOING TASKS
8 | 1 | H | Develop and implement family engagement activities (i.e. family night, parent orientation, etc.). | Superintendents | October 2019 | Ongoing |  |  |  |  | Completed |  | In-person activities were delayed due to Covid. Need to come up with possible virtual options. New painting and furniture delivered for spaces within the hall; painting was delayed due to Covid; Meeting being held to re-open visitation; April 21 youth will be given vaccine which will possibly open things up as well. As a result of the resurgence of Covid -delta this initiative remains on hold. Status is "On Hold".
9 | 2 | B | Include clinicians in multidisciplinary team meetings for medium-to-high-risk juvenile clients. | Ian Long | July 2019 | Ongoing |  |  |  |  | Completed