## Sheet1
DEPT | TASK | START | END | COMPLETION | STATUS
ADM- | Conduct inter-rater reliability assessments on all validated risk/needs assessment tools at least bi-annually. | July 2020 | March 2023 | 50% | On Target
ADM- | Facilitate evidence-based practices briefcase trainings for supervisors. | August 2019 | October 2019 | 100% | Complete
AFS | Implement case management standards.* | January 2018 | December 2021 | 100% | Complete
AFS | Revise and implement an evidence-based rewards and sanctions matrix for adult clients. | January 2018 | June 2021 | 100% | Complete
AFS | Meet and confer with labor union on the potential impacts of the case management standards.* | January 2019 | July 2021 | 100% | Complete
AFS | Conduct quarterly reviews/audits of case plans.* | April 2020 | December 2021 | 100% | Complete
AFS | Ensure case plan templates are in compliance with state and federal guidelines, while also using the risk-need-responsivity (RNR) model for medium and high-risk clients. | May 2020 | April 2021 | 100% | Complete
JFS | Conduct quarterly reviews/audits of case plans. | January 2019 | Ongoing | 100% | Complete
JFS | Develop and implement the case management standards. | April 2020 | December 2021 | 100% | Complete
JFS | Ensure case plan templates are in compliance with state and federal guidelines, while also using the risk-need-responsivity (RNR) model for medium and high-risk clients. | January 2020 | December 2020 | 100% | Complete
JFS | Revise and implement an evidence-based rewards and sanctions matrix for juvenile clients. | January 2020 | June 2021 | 100% | Complete
JFS | Implement case management standards for the juvenile division. | March 2020 | June 2021 | 100% | Complete
JFS | Meet and Confer with labor union on the potential impacts of the case management standards. | April 2020 | November 2021 | 100% | Complete
ADM- | Add the capability of reporting on all benchmarks/outcome measures outlined in the vendor contracts to Tyler Supervision or using other software. | January 2020 | June 2022 | 100% | Complete
ADM- | Develop protocols to oversee contract services and determine role clarification between GSA, fiscal, and contracts staff. | April 2020 | December 2022 | 75% | On Target
ADM- | Develop and implement processes to notify staff of changes in contracted services and service providers on an ongoing basis. | June 2020 | December 2020 | 100% | Complete
ADM- | Use the Correctional Programs Checklist to assess adherence of ACPD programs to evidence-based practices. | June 2020 | December 2023 | 0% | On Target
AFS | Create more in-person opportunities for providers to meet face to face with staff. | April 2019 | October 2020 | 100% | Complete
AFS | Train staff to use Tyler Supervision to communicate with contracted and non-contracted community-based organizations. | October 2019 | December 2020 | 100% | Complete
AFS | Establish policy and procedure guidelines for multidisciplinary team meetings and include them in meetings for high risk clients. | September 2020 | December 2021 | 100% | Complete
JFS | Create more in-person opportunities for providers to meet face to face with staff and direct staff to attend these opportunities. | November 2019 | Ongoing | 100% | Complete
JFS | Establish policy and procedure guidelines for multidisciplinary team meetings. | March 2020 | December 2020 | 100% | Complete
JFS | Train and require staff to use Tyler Supervision to communicate with contracted and non-contracted community-based organizations. | June 2020 | December 2020 | 100% | Complete
ADM- | Develop a policy requiring staff to provide concrete services (bus passes, BART cards, food, etc.) to clients. | June 2018 | October 2020 | 100% | Complete
AFS | Require staff to use Tyler Supervision and its provider portal to make referrals to services in the community and ensure client participation. | January 2019 | December 2020 | 100% | Complete
AFS | Expand the Mental Health Collaborative Court to include adult clients with felony convictions. | November 2019 | December 2021 | 100% | Complete
AFS | Create a specialized mental health caseload unit--specifically SMI and Duel Diagnosis cases. | April 2020 | July 2021 | 100% | Complete
AFS | Establish criteria for specialized caseloads and parameters for case assignments to include the results from assessments.* | March 2020 | December 2020 | 100% | Complete
JFS | Develop a data system to track referrals and outcomes for juveniles not supervised by ACPD. | January 2020 | November 2021 | 100% | Complete
JFS | Add a specialized mental health caseloads. | March 2020 | December 2021 | 100% | Complete
JFS | Establish criteria for specialized caseloads and parameters for case assignments to include the results from assessments. | March 2020 | December 2020 | 100% | Complete
ADM- | Establish a reentry unit. | August 2019 | March 2021 | 100% | Complete
ADM- | Refer clients to eligible services in the community upon discharge. | August 2019 | January 2023 | 75% | On Target
ADM- | Develop a resource packet and distribute to all clients prior to discharge. | June 2020 | April 2021 | 100% | Complete
ADM- | Develop and implement a discharge/transition planning model. | June 2020 | January 2023 | 75% | On Target
ADM- | Require vendors to detail all available transition services for clients upon discharge from probation supervision. | June 2020 | June 2022 | 100% | Complete
ADM- | Evaluate the impact of having staff coached and trained on client outcomes. | February 2022 | February 2023 | 0% | On Target
ADM- | Collect monthly data to assess staff success in addressing client Dynamic Factors. | April 2020 | February 2022 | 100% | Complete
ADM- | Conduct a service gap analysis (map) for entire reentry process bi-annually. | July 2020 | September 2022 | 100% | Complete
ADM- | Identify restorative justice services in Alameda County; Identify service gaps; implement best practices | January 2021 | January 2023 | 25% | On Target
AFS | Develop and implement the Pre-Trial Services Program. | July 2019 | May 2020 | 100% | Complete
AFS | Develop a plan to engage adult clients in civic and community engagement strategies. | January 2021 | January 2022 | 100% | Complete
ADM- | Conduct contract compliance audits of family reunification providers. | July 2020 | January 2022 | 100% | Complete
ADM- | Conduct family focus groups at least bi-annually. | July 2020 | March 2021 | 100% | Complete
AFS | Add family-specific components to case plans. | March 2020 | June 2021 | 100% | Complete
AFS | Develop and implement family engagement activities (i.e. family night, parent orientation, etc.). | November 2019 | March 2021 | 100% | Complete
AFS | Establish collaborative meetings for Adult Field Services clients that include family and other natural supports, including a partner portal. | January 2020 | September 2020 | 100% | Complete
JFac | Develop and implement family engagement activities (i.e. family night, parent orientation, etc.). | October 2019 | Ongoing | 100% | Complete
JFS | Develop and implement family engagement activities (i.e. family night, parent orientation, etc.). | November 2019 | March 2021 | 100% | Complete
JFS | Add family-specific components to case plans. | March 2020 | June 2021 | 100% | Complete
ADM- | Create resources (videos, brochures, interactive website) that explain probation processes and services to clients. | January 2020 | December 2022 | 100% | Complete
AFS | Expand pre-release services for adults reentering from jail and prison, to include referrals completed prior to release. | June 2019 | October 2020 | 100% | Complete
AFS | Establish a Residential Multi-Service Program in Alameda County. | July 2022 | December 2023 | 25% | On Target
AFS | Implement a behavior change model of supervision. | April 2020 | September 2022 | 100% | Complete
JFac | Implement a detention assessment tool in Juvenile Hall. | January 2020 | March 2020 | 100% | Complete
JFac | Implement programming in Juvenile Hall to address criminogenic needs and life skills in ways that are appealing to youth. | January 2020 | December 2020 | 100% | Complete
JFac | Validate the detention assessment tool in Juvenile Hall. | October 2021 | December 2023 | 50% | On Target
JFS | Implement a behavior change model of supervision. | April 2020 | September 2022 | 100% | Complete
JFS | Expand pre-release reach-in services to youth reentering from Camp Sweeney, placement, or Juvenile Hall, to include referrals completed prior to release. | January 2017 | December 2021 | 100% | Complete
ADM- | Create a resource directory on ACPD's home page. | December 2019 | June 2020 | 100% | Complete
ADM- | Train staff on the available resources in the community. | June 2020 | Ongoing | 100% | Complete
ADM- | Implement a dosage-based supervision model. | July 2022 | December 2023 | 0% | On Target
AFS | Expand the CORE to create a “one-stop-shop” that would include services in a variety of reentry areas. | February 2020 | March 2023 | 25% | On Target
AFS | Ensure a comprehensive array of cognitive behavioral intervention services for clients. | April 2020 | December 2022 | 75% | On Target
JFac | Include clinicians in multidisciplinary team meetings for medium-to-high-risk juvenile clients. | July 2019 | Ongoing | 100% | Complete
JFS | Ensure a comprehensive array of cognitive-based intervention services for juvenile clients. | January 2018 | December 2020 | 100% | Complete
JFS | Include clinicians in multidisciplinary team meetings for medium-to-high-risk juvenile clients. | April 2020 | December 2020 | 100% | Complete
JFS | Establish transitional day centers at recreation centers and community-based organizations to provide services to youth. | June 2022 | December 2023 | 100% | Complete
ADM- | Create and hire a reentry housing coordinator position. | June 2019 | February 2021 | 100% | Complete
ADM- | Analyze housing need data from the intake process to better understand client housing needs. | June 2020 | January 2023 | 75% | On Target
ADM- | Hold focus groups with clients to understand their housing needs. | June 2020 | February 2021 | 100% | Complete
ADM- | Hold focus groups with landlords to understand concerns regarding renting to probation clients. | September 2020 | February 2021 | 100% | Complete
ADM- | Increase the number of contracted housing units available for probation clients. | January 2021 | June 2022 | 100% | Complete
AFS | Create and implement a Housing life skills training program which will include housing pamphlets, posters and other resources on housing options available. | March 2020 | March 2022 | 100% | Complete
AFS | Direct staff to offer housing to clients based on need. | April 2020 | December 2020 | 100% | Complete
AFS | Revise the intake process to include an assessments of individuals’ housing needs. | February 2020 | December 2020 | 100% | Complete
JFac | Revise the intake process to include an assessments of juveniles’ housing needs. | February 2020 | December 2020 | 100% | Complete
JFS | Offer housing to clients based on their needs. | January 2020 | Ongoing | 100% | Complete
JFS | Create and implement a housing life skills training program. | March 2020 | March 2022 | 100% | Complete
ADM- | Create a mobile application for clients to access from their smart phones that lists all services provided through the probation department. | November 2019 | December 2022 | 75% | On Target
AFS | Ensure clients are routinely provided their vital documents (CA ID, SS card, Medi-Cal card) upon release from custody. | August 2019 | December 2020 | 100% | Complete
AFS | Provide hygiene kits to clients upon release from custody, at intake and upon request. | September 2019 | Ongoing | 100% | Complete
AFS | Connect with clients while in custody to assess their needs for stabilization pre-release. | January 2020 | December 2020 | 100% | Complete
AFS | Partner with Human Services or Social Services to ensure Medi-Cal is active prior to clients being released from custody. | January 2020 | June 2022 | 100% | Complete
AFS | Establish a process for adult homeless clients to receive vital documents. | February 2020 | December 2020 | 100% | Complete
AFS | Ensure that clients leave custody with a specific plan that addresses their mental and physical health needs. | June 2020 | December 2020 | 100% | Complete
JFS | Establish a process for juvenile homeless clients to receive vital documents. | February 2020 | December 2020 | 100% | Complete
ADM- | Establish a critical incident stress management and peer support program to be staffed by ACPD personnel. | July 2022 | September 2023 | 75% | On Target
ADM- | Reclassify administrative specialist II to safety officer. | July 2019 | November 2019 | 100% | Complete
AFS | Establish a weapons and safety committee to review current safety equipment and weapons and recommend new items. | April 2020 | March 2021 | 100% | Complete
ADM- | Analyze data on service usage and outcomes for juvenile clients and at-promise youth using Tyler Supervision (provider portal being stood up), Mobius (working with them on needed changes), and Results First. | August 2020 | December 2021 | 75% | On Target
ADM- | Create a dedicated recruitment team. | January 2021 | December 2022 | 75% | On Target
ADM- | Develop a college student intern program under the Office of Human Resources. | July 2022 | December 2023 | 25% | On Target
ADM- | Develop a tool to track the progress of recruitment efforts and measure recruitment of Affirmative Action Plan groups. | June 2019 | December 2020 | 100% | Complete
ADM- | Publicize job openings through career fairs, schools, and social media. | June 2019 | December 2019 | 100% | Complete
ADM- | Revamp the new employee orientation and conduct it within 90 days of hire. | June 2019 | July 2019 | 100% | Complete
ADM- | Revamp Volunteers in Probation (VIP) program. | July 2022 | December 2023 | 25% | On Target
ADM- | Develop tool to track probationary and tenure statuses and retention of employees based on years with ACPD. | July 2019 | December 2020 | 100% | Complete
ADM- | Establish performance standards for each job classification within ACPD. | July 2019 | December 2022 | 75% | On Target
ADM- | Assign recruitment committee members as mentors to new employees during their probationary period. | December 2019 | December 2022 | 50% | On Target
ADM- | Announce training and conference opportunities as they become available. | January 2017 | Ongoing | 100% | Complete
ADM- | Establish a professional development academy for line and mid-level staff. | February 2018 | October 2019 | 100% | Complete
ADM- | Offer elective trainings that address core competency requirements. | January 2019 | December 2022 | 25% | On Target
ADM- | Assess employees’ professional development needs and coordinate annual course offerings to address those needs. | June 2019 | December 2022 | 50% | On Target
ADM- | Create a duties statement for every staff position. | June 2019 | December 2021 | 75% | On Target
ADM- | Create a manual on the core competencies associated with the knowledge, skills, and abilities (KSAs) for all 81 job classifications. | June 2019 | December 2022 | 50% | On Target
ADM- | Use annual performance evaluation to identify core competencies that need to be addressed through professional development. | June 2019 | December 2022 | 50% | On Target
ADM- | Establish a leadership academy for executive managers. | July 2019 | December 2023 | 75% | On Target
ADM- | Offer a new supervisors academy within first 90 days of hire or promotion. | January 2020 | December 2020 | 100% | Complete
ADM- | Establish a formal process for ongoing supervisor-employee progress reviews between annual performance evaluations. | February 2020 | December 2023 | 25% | On Target
AFS | Create unit-specific performance measures and ensure applicable measures are consistent across divisions. | April 2020 | December 2020 | 100% | Complete
JFS | Create unit-specific performance measures and ensure applicable measures are consistent across divisions. | April 2020 | December 2020 | 100% | Complete
ADM- | Implement effective reminder system for employee performance evaluation. | November 2019 | December 2022 | 75% | On Target
ADM- | Implement interim effective reminder system for employee performance evaluation. | November 2019 | December 2020 | 100% | Complete
ADM- | Survey staff to measure the effectiveness of recognition and appreciation programs. | December 2019 | December 2020 | 100% | Complete
ADM- | Establish and launch a new staff appreciation component to current recognition program. | January 2020 | March 2022 | 100% | Complete
ADM- | Establish consistent appreciation efforts to acknowledge and celebrate ACPD employees. | January 2020 | December 2023 | 25% | On Target
ADM- | Revise annual performance evaluation process and policy. | February 2020 | June 2021 | 100% | Complete
ADM- | Identify and track policy priorities on an ongoing basis by division. | January 2019 | August 2019 | 100% | Complete
ADM- | Formalize a process to identify training needs early in the policy development stage and prior to routing the policy to County Labor. | January 2019 | October 2019 | 100% | Complete
ADM- | Research and implement a policy management software. | June 2019 | March 2020 | 100% | Complete
ADM- | Track policies identified for development. | June 2019 | December 2020 | 100% | Complete
ADM- | Track time associated with the stages of policy development. | June 2019 | November 2021 | 100% | Complete
ADM- | Revise the policy and procedures intranet page to include a more accessible layout and improved organization of policy manuals. | November 2019 | September 2020 | 100% | Complete
ADM- | Fully staff the Policy Unit. | January 2020 | September 2020 | 100% | Complete
ADM- | Develop a process for reporting implementation (training and dissemination) of new policies to the Policy Unit. | March 2020 | December 2020 | 100% | Complete
ADM- | Develop division-specific procedures, including accountability measures, to ensure staff are trained on new policies. | March 2020 | December 2020 | 100% | Complete
ADM- | Hire a communications director. | December 2019 | September 2022 | 25% | On Target
ADM- | Create a departmental newsletter. | January 2020 | December 2020 | 100% | Complete
ADM- | Develop a communication policy that includes social media. | March 2020 | December 2022 | 75% | On Target
ADM- | Develop and administer annual external stakeholder survey. | August 2020 | September 2022 | 75% | On Target
ADM- | Develop a communication workgroup that would oversee the annual staff survey. | December 2020 | June 2021 | 100% | Complete
ADM- | Create and implement a communication matrix/system. | January 2021 | June 2022 | 0% | On Target
ADM- | Develop and implement an internal probation bulletin board page that would include probation-related research articles, job tutorials, standard operating procedures, officer-of-the-day calendar for all divisions, locations, and units, unit rosters and contact information, staff meeting agendas & minutes, and professional development training opportunities. | January 2021 | January 2022 | 100% | Complete
ADM- | Establish methods for the dynamic exchange of information between units and divisions. | January 2021 | June 2022 | 0% | On Target
ADM- | Create a research unit. | November 2018 | November 2019 | 100% | Complete
ADM- | Develop and report on strategic plan performance measurement. | April 2019 | Ongoing | 100% | Complete
ADM- | Hire an administrator for Tyler Supervision. | November 2019 | December 2020 | 100% | Complete
ADM- | Perform quality assurance checks on data from Tyler Supervision. | November 2019 | June 2020 | 100% | Complete
ADM- | Develop and implement PROBSTAT. | December 2019 | December 2020 | 100% | Complete
ADM- | Establish a quality assurance process for all publicly-reported data. | December 2019 | June 2020 | 100% | Complete
ADM- | Create a quality assurance unit. | January 2020 | December 2020 | 100% | Complete
ADM- | Develop quality assurance protocols and procedures.* | January 2020 | March 2021 | 100% | Complete
ADM- | Establish internal expert on PowerBI for ongoing support. | January 2020 | December 2020 | 100% | Complete
ADM- | Provide PowerBi licenses for all relevant classifications and develop advanced training and support systems. | January 2020 | December 2020 | 100% | Complete
ADM- | Provide training to units on performance measurement. | January 2020 | December 2020 | 100% | Complete
ADM- | Regularly publish performance measure data internally and externally. | May 2020 | December 2022 | 75% | On Target
ADM- | Create unit specific and job-specific dashboards. | June 2020 | December 2020 | 100% | Complete
AFS | Fully implement Tyler Supervision. | January 2019 | June 2020 | 100% | Complete
AFS | Hold standing meetings with labor unions regarding Tyler Supervision and COMPAS implementation. | August 2020 | April 2021 | 100% | Complete
JFac | Establish Tyler Supervision core team for Juvenile Facilities. | January 2020 | June 2020 | 100% | Complete
JFac | Fully implement Tyler Supervision. | August 2020 | December 2020 | 100% | Complete
JFS | Establish Tyler Supervision Core Team for Juvenile Field Services. | October 2019 | December 2019 | 100% | Complete
JFS | Fully implement Tyler Supervision. | August 2020 | December 2020 | 100% | Complete
JFS | Hold standing meetings with labor unions regarding TS implementation. | August 2020 | April 2021 | 100% | Complete
ADM- | Develop corrective action plans for contracted providers that don't meet their reporting requirements. | October 2018 | Ongoing | 100% | Complete
ADM- | Establish consistent performance measures and definitions in RFPs and contracts based on type of service being provided. | October 2018 | December 2020 | 100% | Complete
ADM- | Solicit input from Research and Evidence-based Practices Units on development of new RFPs. | October 2018 | Ongoing | 100% | Complete
ADM- | Create a contracts unit. | November 2018 | January 2020 | 100% | Complete
ADM- | Create an evidence-based practices unit. | November 2018 | December 2021 | 100% | Complete
ADM- | Establish necessary points of collaboration between the EBP Unit, Contracts Unit, and Research Unit. | November 2018 | June 2020 | 100% | Complete
ADM- | Participate in the Alameda County Results First initiative with other criminal justice partners. | December 2018 | July 2020 | 100% | Complete
ADM- | Develop a policy for conducting internal research studies, including access to external research databases. | November 2019 | December 2020 | 100% | Complete
ADM- | Provide ongoing training to staff on evidence-based practices. | December 2019 | March 2022 | 100% | Complete
ADM- | Develop a standardized process for collecting and reporting on performance measure data from contracted providers. | June 2020 | September 2022 | 100% | On Target
ADM- | Collect quantitative data to demonstrate skill acquisition and outcomes related to training staff in evidence-based practices. | February 2022 | February 2023 | 0% | On Target
ADM- | Develop a survey that allows clients to provide feedback on provider services and require contractors to administer survey. | January 2021 | June 2022 | 100% | Complete
ADM- | Continue to produce annual Realignment reports and produce fact sheets to disseminate publicly. | November 2018 | June 2022 | 100% | Complete
ADM- | Conduct gap analysis on needs related to data entry, administrative support, and software and systems. | January 2020 | December 2020 | 100% | Complete
ADM- | Develop data dictionary for all data dashboards released. | January 2020 | June 2021 | 100% | Complete
ADM- | Develop definitions and process for reporting on client outcomes, including recidivism. | January 2020 | December 2020 | 100% | Complete
ADM- | Establish process to continuously monitor and update data collection, reporting, and data collection needs. | January 2020 | January 2021 | 100% | Complete
ADM- | Use data to evaluate outcomes against departmental performance measures. | January 2020 | December 2020 | 100% | Complete
ADM- | Develop a process to track and measure internal data requests. | April 2020 | April 2021 | 100% | Complete
ADM- | Hold regular collaboration meetings between legislation, policy, research, and division reps to discuss upcoming data needs. | June 2020 | June 2022 | 100% | Complete
ADM- | Create matrix tracking all ACPD initiatives with external partners. | November 2018 | April 2019 | 100% | Complete
ADM- | Develop a shared vision of public safety based on feedback from and collaboration with JJDPC and CCPEC. | January 2020 | Ongoing | 100% | Complete
ADM- | Provide information about publicly available data and data request processes on ACPD website. | October 2019 | December 2019 | 100% | Complete
ADM- | Upload and regularly update information on ACPD's website and intranet. | October 2019 | Ongoing | 100% | Complete
ADM- | Develop policy and process for sharing data externally (through website, DSAs, etc.) | January 2020 | December 2021 | 100% | On Target
ADM- | Establish policies, procedures, and oversight for data-sharing agreements with external agencies. | January 2020 | December 2021 | 100% | Complete
ADM- | Develop and implement an anonymous client survey that solicits feedback from clients about their experience on probation and how ACPD can improve its service delivery. | June 2019 | December 2022 | 75% | On Target
ADM- | Analyze data on adult service usage and outcomes from service providers using Tyler Supervision. | June 2020 | June 2022 | 100% | Complete
ADM- | Analyze data on service usage and outcomes for juvenile clients and at-promise youth using Tyler Supervision (provider portal being stood up), Mobius (working with them on needed changes), and Results First. | August 2020 | December 2021 | 100% | Complete
AFS | Deploy Prime. | January 2019 | January 2020 | 100% | Complete
AFS | Deploy Tyler/Enterprise Supervision Supervision App. | August 2020 | December 2022 | 75% | On Target
JFac | Provide tablets to all youth in Juvenile Hall and Camp Sweeney for academic and incentive programming. | September 2019 | February 2020 | 100% | Complete
JFS | Deploy Prime. | August 2020 | December 2021 | 25% | On Target
ADM- | Add resources regarding victims services to ACPD website. | November 2019 | December 2019 | 100% | Complete
ADM- | Assign victim services liaison responsibilities to juvenile and adult services ombudsman. | January 2021 | June 2022 | 0% | On Target
ADM- | Expand departmental policies related to victim support, including notification of victims rights and creating victim safety plans. | January 2021 | June 2022 | 0% | On Target
ADM- | Perform a gap analysis on policy, training, initiatives, service contracts, etc. related to victim support services. | January 2021 | June 2022 | 0% | On Target
AFS | Develop a victim support model for ACPD in coordination with the District Attorney's Office. Expand departmental policies related to victim support, including notification of victims rights and defining expectations around victim safety plans. | January 2020 | September 2022 | 100% | Complete
AFS | Expand departmental policies related to victim support, including notification of victims rights and defining expectations around victim safety plans. | January 2020 | September 2022 | 100% | Complete
AFS | Develop auditing process for batterers intervention programs. | January 2020 | December 2020 | 100% | Complete